Disability network Business Acumen Learning Collaborative	State Team:  MISSOURI

Action Plan Status Report					Month Reported:  January 2, 2018

Please complete and upload to the disability network Business Acumen Learning Collaborative Dropbox one week prior to your scheduled check-in call.  Complete an action plan status report for each priority are you team is working on.

| Overall Aim: | Create an integrated system that demonstrates improved health outcomes, reduced costs, and increased stakeholder satisfaction through building collaboration and CBO capacity for people with IDD who are aging and/or living with co-occurring conditions. |
| --- | --- |
| Priority Area #1 | Strengthen CBO capacity. |
| Improvements on Overall Aim Related to this Priority Area: | Effectively identifying information needed and building framework to support CBOs work. |

| Strategies | Activities |  | Barriers/Mitigation |  | Result |
| --- | --- | --- | --- | --- | --- |
| From Action Plan | Completed What we’ve done | Planned What we’re going to do | Challenges/Surprises | Solutions to Challenges | Effective – Continue/complete Not Effective – Research/revise |
| A. Develop system-wide value-based health outcomes and demonstrate ROI. |  | Gather value-based outcomes currently required by federal and state funders and MCOs. |  |  |  |
| B. Build stakeholder engagement. | Develop list of topics for further study along with subject matter experts who can present to the LC. | Develop agendas based on topics and schedule guest speakers. | Scheduling presentations. Alignment so information flows and informs discussion for next meeting/topics. | Identified who/what topics could be done by conference calls in between meetings. | We have some presenters scheduled during regular meetings and setting up conference calls with others in between to keep things moving at meaningful pace. |
|  | Develop questions to be addressed by presenters and provide to speakers at least 2 weeks prior to meeting. | Developed MCO and CMHC questions at last meeting. Added questions from Tool Kit and other materials collected and CMHC questions for our first presenter are being circulated to team. |  |  |  |
| C. Develop opportunity for innovation projects. | Identify contacts for local partnerships. | In development. Includes mission/purpose of the group, territory maps and contact information. |  |  |  |
|  | Gather information on alternative funding opportunities/programs. | Have gathered information on PACE program and spoken with consultants intimately familiar with PACE. Also received recommendation to look into Pennsylvania’s ODP Program and Delaware’s Promise Program (1115). |  |  |  |